## Slide 1: El Salvador
Support the implementation of actions to promote youth employment in El Salvador
SIDA/YEP

## Slide 2: Intervention
Strengthen articulation and coordination for implementation
Promotion strategy
Articulating public services
Framework to promote YE
First employment
Capacity Building EO and WO
Young Leaderships
Coordination spaces
“One stop shop” model
Entrepreneurship services
Institutionalization of promote YEP

## Slide 3: Logframe
Output 1: Strengthened the capacities of the Salvadorean government to promote articulation and coordination between stakeholders facing the implementation and dissemination of actions to promote employment for young women and men.
  Strategy to promote decent work for young people implemented.
  Creation and / or strengthening of institutional spaces for the implementation of measures envisaged in the project.
Output 2: Articulating proposal of the MTPS services and other instances for models "one stop shop" of attention for young people.
  Scheme to provide services for youth employment policy for youth population under the “one stop shop” model, established under RENACEMPLEO (Employment public service).

## Slide 4: Logframe
Output 3: Developed a framework for the promotion of youth employment through internships, apprenticeship and entrepreneurship.
  Pilot training program and work as part of internships, apprentice contract and employability training for work in coordination with relevant government agencies, as well as OT and SO.
  Program promotion and support youth entrepreneurship, with special emphasis on the needs of young women.
Output 4: Capacities of employers and workers organizations in the promotion of youth employment from the perspective of equal opportunities between men and women have been strengthened.
  Training program aimed at executive committees and specialized units (secretaries) of youth in OT and SO.
  Strengthening youth employment units in OT and SO.

## Slide 5: Achievements by output
Output 1:
  A participative construction process of the “promotion strategy of public employment service for young people” has started. An Advisory Committee was created and functioning. Is compose by Labor ministry, National Youth Institute, Institute for the Development of Women.
  Have been integrated work processes, through synergy whit YE/Gender project SIDA funded (Eradication of gender stereotypes on youth employment promotion).
  Creation and operation of space for inter-institutional coordination, for the Implementation of the “Law for the Creation of the First Employment of the Young Persons in the Private Sector” (Legislative Decree No. 57 dated July 12th 2012). Compose by LM, FM, SSI.

## Slide 6: Achievements by output
Output 2:
  Construction process of a model to integration of the service on RENACEMPLEO and entrepreneurship service for young people, has started with LM and National Institute for youth.

## Slide 7: Achievements by output
Output 3:
  Program to Promote and support youth entrepreneurship In collaboration with the National Association of Private Enterprise, has started. (100 young people -23 to 29 years old- from three Municipalities). As a first exercise of this kind, look for build the capacities on EO to provide entrepreneurship services for young people. In addition, ANEP will create an operating unit, which will be responsible for the implementation of the strategies established in this program.

## Slide 8: Achievements by output
Output 4:
  Identify together with The country's main unions, the priorities for the strengthening of the capacities for the promotion of youth employment from Workers' Organizations.(Two national workshops and consultation process).
  Capacity Building Program in promoting youth employment from young leaders in the WO, developed and validated (will start on middle of April).

## Slide 9: Project contribution to Indicator 2.5
Measurement criteria:
Youth employment is a priority of national development strategies or national employment policies.
  Government, EO and WO incorporate on their priorities and strategically framework the YE issues.
  Promote the institutionalization of programs and initiatives on YE
National plans promoting youth employment are developed by the government and the social partners and contain priority measures as well as human and financial resources for their implementation.
  Enhance the implementation of YE programs and initiatives includes on National Plan on Youth Employment. (Firs Employment, Promotion Strategy, Entrepreneurship services, One Stop Shop model)
An information dissemination, awareness-raising, training or outreach strategy on youth employment is implemented, as documented through evidence of, for example, establishment of hotlines and brochures, training courses, services or recruitment campaigns by employers’ or workers’ organizations.
  Deliver a promotion strategy built with the stakeholders including an important component of gender mainstreaming.