## Slide 1: MAINSTREAMING CHILD LABOUR IN EDUCATION:TACKLE PROJECT 2008 TO 2013-ZAMBIA
Presented by Dr. Seti Venus and Mr Silungwe West
BELGIUM,BRUSSELS, FROM SECOND TO THIRD JULY, 2013

## Slide 2: KRA/FOCUS OF THE PROGRAMME
To come up with Improved Country level Child Labour and Education Legal Framework enhancement in Zambia through support.
Institutional Capacity strengthening in order to design strategies meant to eliminate Child Labour.
Develop Actions to combat Child Labour and Models that could be useful in implementing Child Labour Programmes
Enhancement of knowledge base and Net Work on Child Labour and Education advocacy and sharing or designing good practices.

## Slide 3: PROJECT PERFORMANCE
The project made steady progress and as a result the following successes were achieved in the targeted four key result areas:
KEY RESULT AREA ONE : REVIEWING POLICY AND LEGAL FRAMEWORKS
In preparing country level frameworks and strengthening them, the following activities were undertaken:
Enhancement of the Employment of Young Persons & Children Act
Child Labour Policy

## Slide 4: PROJECT PERFORMANCE Cont…
Zambia Decent Work Country Programme Priority on CL elimination
National Action Plan for elimination of Worst Forms of CL
Statutory Instrument on hazardous Work developed
Review of National Education Policy (access, quality, efficiency and equity) and Education Act
Enhancement of the Free Primary Education Policy

## Slide 5: PROJECT PERFORMANCE Cont…
The Project organised a stakeholder’s consultative meeting on child labour and educational legal frameworks. Presentations focussed on hazardous Labour, the Education Act, and the Ant-Human Trafficking Act. The meeting was held on 20th June,2012.
Supported the process of reviewing Labour Laws.

## Slide 6: KEY RESULT AREA TWO: CAPACITY BUILDING
In strengthening institutional capacity leading to improved ability to formulate and implement child labour strategies the following activities were done:
Ministry of Education officials were trained in SCREAM: Supporting Children’s rights through education, the arts and the media in September, 2008.
Teachers were trained on child labour, children’s rights, psychosocial counselling and other aspects affecting the child. The training has had a positive effect on the integration of child labour concerns at school level and has facilitated the institutional support for children prevented and withdrawn from child labour

## Slide 7: KEY RESULT AREA TWO: CAPACITY BUILDING (Cont’d)
The Project facilitated the training of two (2) MESVTEE officials as resource persons in child labour and education in Johannesburg in May, 2011.
Participated in organising a regional training for stake holders in child labour and education with representation from all Directorates at Headquarters and all Provincial Education Standards Officers (PESOs) from provinces.
On 5th March, 2013 a briefing meeting for Senior Management Team at MESVTEE headquarters was held to brief them on the background of the project and some activities undertaken on child labour and

## Slide 8: KEY RESULT AREA TWO: CAPACITY BUILDING (Cont’d)
Education.
In April, 2013 the project supported provincial trainings for four (4) Provincial Teams on education and child labour.
Trained officials from Central Statistics Office, Ministry of Labour and Education in Child Labour and data collection and analysis
Partner capacity strengthening on Child Labour Policy and Action Plan targeting implementing partners in 2011

## Slide 9: KEY RESULT AREA 3: TARGETED ACTIONS TO COMBAT CHILD LABOUR DESIGNED AND IMPLEMENTED TO DEVELOP EFFECTIVE DEMONSTRATION MODELS
In an effort to implement child labour, the following actions were undertaken:
Number of children withdrawn= 1133
Prevented= 1450
The Government has co-operated with partners working on combating child labour through education by supporting withdrawn children in school and preventing others from child labour.
Poverty reduction interventions and reduction of education barriers such as:

## Slide 10: TARGETED ACTIONS TO COMBAT CHILD LABOUR DESIGNED AND IMPLEMENTED TO DEVELOP EFFECTIVE DEMONSTRATION MODELS (Cont’d)
Re-enforcing the Free Primary Education Policy
An ambitious program of infrastructure development targeted at reducing the distance between schools to that of 5km;
Abolishment of grade 7 and 9 examination fees;
Support to community schools in form of grants and teaching learning materials
Monitoring of gender parity index at all levels
Annual recruitment of teachers for public schools (5000 net and replacements every year)

## Slide 11: KEY RESULT AREA 3: TARGETED ACTIONS TO COMBAT CHILD LABOUR DESIGNED AND IMPLEMENTED TO DEVELOP EFFECTIVE DEMONSTRATION MODELS (Cont’d)
Expanded levels of School Health and Nutrition and water and sanitation programs
Food security pack and
Public Social Welfare Assistance Schemes
Creation of the District Child Labour Committees
Development of the M & E and Resource mobilisation strategy
Development of the Understanding Children’s Work Booklet
Developed manuals on forced labour and human trafficking
Supported the Policy and Law consultative process resulting in the development of the Sixth National Development Plan .

## Slide 12: KEY RESULT AREA 4: ENHANCE KNOWLEDGE BASE AND NET WORKS ON CHILD LABOUR AND EDUCATION THROUGH IMPROVED ADVOCACY AND DISSEMINATION OF GOOD PRACTICES
In an effort to improve advocacy and dissemination of good practices to enhance knowledge base and net works on child labour and education, the following activities were undertaken:
Establishment of an advocacy group for free and compulsory education in Zambia;
From 2008 to 2013, schools participate in the World Day Against Child Labour (WDACL) through debates, quizzes, drama, music performances, media interviews, sensitisation match past and awards presentation to

## Slide 13: KEY RESULT AREA 4: ENHANCE KNOWLEDGE BASE AND NET WORKS ON CHILD LABOUR AND EDUCATION THROUGH IMPROVED ADVOCACY AND DISSERMINATION OF GOOD PRACTICES( Cont’d)
Winning schools and individuals. The climax of the event is done on 12th June every year. In this year’s event in addition to members of the community , political and traditional leaders (chiefs) were also invited to the function.
On best practices, the involvement of political leaders, senior government officials, social partners and traditional leaders(chiefs) resulted in the successful implementation of the program.
Support to the Labour Force Survey of 2012 by integrating child labour modules

## Slide 15: RECOMMENDATION
The Programme meant well and it should be renewed.
It would also suffice if funding consideration focussed towards the formulation of the child labour free zones in various parts of the country(Zambia).
Roll out the programme to other provinces that were not targeted

## Slide 17
Number of children withdrawn= 1133
Prevented= 1450