## Slide 1: RBM tools: Evaluability Assessment, Quality and Appraisal Mechanisms (TC projects, DWCPs)

## Slide 2: What is Results-based management (RBM)?
Managing with the result as the point of departure
Start with the measurable ‘end’ clearly articulated and mobilize all resources towards achieving this ‘end’!
Focus on results rather than activities and outputs
Define success and work to achieve it!

## Slide 3: Pillars of RBM
the definition of strategic goals which provide a focus for action;
the specification of expected results which contribute to these goals and align programmes, processes and resources behind them;
ongoing monitoring and assessment of performance, integrating lessons learned into future planning; and
improved accountability based on continuous feedback to improve performance.

## Slide 4: Some RBM Tools at the ILO
Evaluability Assessment
DWCP Quality Assurance Mechanism (QAM)
TC Appraisal Mechanism
… they all support “ an approach that directs organizational processes, resources, products and services towards the achievement of measurable results” *
* Definition from ILO Office Directive IGDS 112 (version 1) , 25 August 2009

## Slide 5
Evaluability Assessment

## Slide 6: What is ‘evaluability’?
Extent to which an activity or a program can be evaluated in a reliable credible manner
Notes: 6

## Slide 7: How does Evaluability relate to RBM?
Evaluability ensures that key elements for RBM are included at the point of departure
Start with the measurable ‘end’ clearly articulated and with measurable indicators towards achieving this ‘end’!
Focus on results rather than activities and outputs

## Slide 8: Why Evaluability?
To improve management effectiveness and accountability
define realistic expected results
monitor progress toward the achievement of expected results
evaluate and report on performance
integrate lessons learned into management decisions

## Slide 9
Formulating SMART objectives
Setting targets
Selecting indicators
Performance
Measurement
Strategic
Planning
Performance
Management
Key phases of RBM and Evaluability
Evaluation and Lessons
Using performance information for managing
Monitoring performance data
Reviewing & reporting performance
Notes: 9
9

## Slide 10: Evaluability criteria
To begin, the diagnosis of a problem results in the formulation of a series of Objectives which set out a path towards desired change…
…where progress towards this change can be estimated by suitable Indicators…
…which require accurate Baseline information about where the project is starting from…
…while Milestones provide a series of yardsticks on the road towards meeting the objectives…
…in the meantime, effective Risk Management gives the greatest chance the project can be fully executed…
…that all translates into a well-defined Monitoring and Evaluation system.
Notes: 10
For the risks and assumptions, the evaluability assessment incorporates the following as a key element for the analysis:
The conditions necessary for the execution of the programme and its project and the achievement of the objectives are identified
Follow-up actions for mitigating the impact of the risks and for monitoring the validity of the assumptions and risks are identified
The evaluability instrument asks users if there has been...
Identification of principal restrictions to achieving outcomes
Identification of risks associated with each strategy option OR Identification of risks associated with achieving project outcomes
A clear definition of risk mitigation measures, supported by theory, logic, empirical evidence and/or past ILO experience

## Slide 11: RBM Tools
Results | Indicators (With baseline) | Data Sources (MoV) | Collection Methods | Collection Frequency | Responsible
Impact |  |  |  |  | 
Outcomes | Indicator Baseline |  |  |  | 
Outputs | Indicator Baseline |  |  |  | 
Activities |  |  |  |  | 
Levels of Objectives (Intervention Logic) | Verifiable Indicators | Means of Verification | Critical Assumptions (and Risks)
Impact |  |  | 
Outcomes |  |  | 
Outputs |  |  | 
Activities |  |  | 
From Evaluabilty Assessments to improved results matrix to M & E Framework
Evaluability Assessment
Notes: Last updated 13 May 2009
11

## Slide 12
Levels | Verifiable Indicators (With Baselines) | Means of Verification (Data Sources and Collection Methods) | Critical Assumptions (and Risks)
Impact |  |  | 
Outcomes |  |  | 
Outputs |  |  | 
Activities |  |  | 
From logframe formulation to planning
What | When |  | Who |  | 
Outputs and main activities | Implementation period |  | Main partners | Main staff/ entity responsible for output | Other staff/ entities responsible
Priority: Outcome: |  |  |  |  | 
Activity 1.1.1.1 |  |  |  |  | 
DWCP Implementation
Plan
DWCP M&E Plan
Priority 1: |  |  |  |  |  | 
Outcome 1.1: |  | Main assumptions: |  |  |  | 
Indicators | Baselines | Targets | Milestones |  |  | 
 |  |  | 2009 | 2010 | 2011 | 2012
Tools to be used: DWCP M&E Plan and Implementation Plan
links to TC Implementation Plan
links to TC Performance Plan

## Slide 13: Tools to be used: DWCP Implementation Plan
WHAT |  |  | WHEN |  | WHO |  | HOW | 
Outputs | Output weighting (%) | Planned activities | Timeframe |  | Responsibility | Partners | Estimated costs by activity | 
 |  |  | Start date | Completion date |  |  | Staff costs | Non-staff
Immediate Objective 1: |  |  |  |  |  |  |  | 
Output |  | Activity |  |  |  |  |  | 
 |  | Activity |  |  |  |  |  | 
links to
TC Impl. Plan
What | When |  | Who |  |  | Funded how |  |  |  |  |  | 
Outputs and main activities | Implementation period |  | Main partners | Main staff/ entity responsible for output | Other staff/ entities responsible | Estimated costs by output | Allocated funds by output |  |  |  | Resource gap | 
 | Start date | End date |  |  |  |  | US$ | Source [1] | Origin [2] | Time [3] | US$ | Potential Source [4]
Priority 1: |  |  |  |  |  |  |  |  |  |  |  | 
Outcome 1.1: |  |  |  |  |  |  |  |  |  |  |  | 
Output 1.1.1: |  |  |  |  |  |  |  |  |  |  |  | 
Activity 1.1.1.1: |  |  |  |  |  |  |  |  |  |  |  | 
Activity 1.1.1.2: |  |  |  |  |  |  |  |  |  |  |  | 
Repeat for each outcome and output as appropriate. |  |  |  |  |  |  |  |  |  |  |  | 
1] RB, RBTC, PSI, XBTC, RBSA [2] e.g. SRO, HQ dept X, Project Y [3] e.g. 2008-09, June 08-May 10 [4]e.g.RBSA, XBTC. The name of the project should be included in this column. |  |  |  |  |  |  |  |  |  |  |  | 
DWCP
Impl. Plan
Notes: Kidest
Last updated 13 May 2009
13

## Slide 14: Tools to be used: DWCP M&E Plan
Immediate Objective: |  |  |  |  |  | 
Indicators | Baseline + year | Target | Milestones |  |  | 
 |  |  | Period 1 | Period 2 | Period 3 | Period 4
links to TC Performance Plan
Priority 1: |  |  |  |  |  | 
Outcome 1.1: |  | Main assumptions: |  |  |  | 
Indicators | Baselines | Targets | Milestones |  |  | 
 |  |  | 2009 | 2010 | 2011 | 2012
DWCP M&E
Plan
Notes: Last updated 13 May 2009
14

## Slide 15: Evaluability Assessment toolkit
Logical model / log frame
Implementation plans
1
2
Monitoring and Evaluation plans
3
Strategic framework

## Slide 16
Outcomes
Impacts
Outputs
Activities
Inputs
Conceptual Logic Model
Notes: 16
16
16

## Slide 17: Outcome of retrofitting
DWCPs
Well-developed M&E system
Clear objectives
SMART indicators
Risks and assumptions identified
Baselines
Time-bound milestones
EVALUABLE
For Effective monitoring and evaluations
Notes: Last updated 13 May 2009
17

## Slide 18
DWCP Quality Assurance Mechanism (QAM)

## Slide 19: What is QAM?
Process aimed to ensure:
Quality and coherence across DWCPs
Statement of tangible results, through the use of RBM
Clear ownership and accountability
Tripartite involvement in DWCPs’ formulation and implementation
Sustainability of DWCPs through a well-designed, resourced plan

## Slide 20: QAM Background and Status
Introduced in the ILO in 2007
Assessed in May 2008 for effectiveness
Based on lessons learnt, currently under revision to:
  Streamline management processes related to QAM
  Reinforce the integral approach envisioned in the SJD
  Include evaluability components into QAM
  Review and modify current QAM support groups
  Enhance existing templates/tools
  Clarify roles and accountabilities between HQ, ROs and COs

## Slide 21: Proposed New QAM Steps
Conceived as a comprehensive process, not only as the punctual application of a checklist.
*Proposal to be discussed with the Regions. Planning of discussions in progress.
1. FORMULATION
Country Office
Apply quality assurance
tool
2. APPRAISAL
Regional Office
Apply evaluability tool
3. REVIEW
Headquarters
Check Office-wide
policies inclusion
Notes: HOW?

## Slide 22
TC Appraisal Mechanism

## Slide 23: Technical Cooperation in the context of DWCPs
Results…at the country level:
TC
Country Programme
Outcomes
TC
TC
UNDAF /
One UN

## Slide 24: Technical Cooperation Appraisal Mechanism
Appraisal: “an overall assessment of the relevance, feasibility and potential sustainability of a development intervention prior to a decision of funding”
OECD DAC Glossary of Key Terms in Evaluation and Results Based Management
Aim: to ensure the quality-at-entry of XBTC projects and programmes

## Slide 25: Appraisal checks for
Relevance &
strategic fit
Tripartism &
Social dialogue
Project logic
Evaluability and
M&E
Sustainability
and feasibility
Gender
mainstreaming
APPRAISED

## Slide 26: Appraisal process
3
Appraisal and endorsement by:
- The technical backstopping unit(s), if the proposal originates in the field
- OR The relevant field office director, if the proposal originates from headquarters
Appraisal and endorsement by:
- the responsible Regional Office (RO)
Appraisal report issued when quality standards satisfied
Appraisal comments / dialogue
2
1
Project originator:
- Drafts proposal and performs initial quality control through a self-appraisal.
- Reworks the proposal according to comments received
RO sends proposal to PARDEV for final appraisal

## Slide 27: Survey on TC Appraisal Mechanism
Reviewed after its first 6 months in operation
Check on stakeholder perceptions (project designers; field, regional & technical unit appraisers)
100% of respondents said appraisal is an important part of project cycle
44% said appraisal had helped enhance proposal quality to a great extent. 56% said it enhanced quality to a certain extent. Nobody felt the quality of their proposal hadn’t been enhanced.
Approximately ¾ of respondents did not experience any bottlenecks or delays in the appraisal mechanism
Appraisal was overwhelmingly seen as value-added