## Sheet1
3-D Client Value Assessment Workplan
How to use this document? The objective of this Workplan Sample is to support the planning and monitoring of a 3-D client value assessment. Further details on the different steps described below can be found in the 3-D Technical Guide. The timelines shown below are meant to provide an idea of order of operations, and should be adapted to each client value assessment, based on the scope of the project and resources available.
Weeks
Ref. | Task | Responsible | Start date | End Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
Step 1. Project planning
1.1 | Gather and analyze general information on context and product | XX | MM.DD.YY | MM.DD.YY | [12 empty] | .
1.2 | Identify key stakeholders and contact points | XX | MM.DD.YY | MM.DD.YY
1.3 | Discuss objectives, expectations and timelines with key stakeholders | XX | MM.DD.YY | MM.DD.YY
1.4 | Refine project scope and objectives | XX | MM.DD.YY | MM.DD.YY
1.5 | Identify and address potential additional resources needed (e.g, local surveyors) | XX | MM.DD.YY | MM.DD.YY
1.6 | Create final workplan | XX | MM.DD.YY | MM.DD.YY
Step 2. Preparation
2.1 | Discuss administrative data needs and availability with key stakeholders | XX | MM.DD.YY | MM.DD.YY | [12 empty] | .
2.2 | Identify relevant sources for each document needed and define timelines | XX | MM.DD.YY | MM.DD.YY
2.3 | Send written data requests to relevant stakeholders | XX | MM.DD.YY | MM.DD.YY
2.4 | Research information to be obtained from external sources (research institutes, government, etc) | XX | MM.DD.YY | MM.DD.YY
2.5 | Sampling for farmers, staff and agents interviews | XX | MM.DD.YY | MM.DD.YY
2.6 | Preparation of survey / interview instruments | XX | MM.DD.YY | MM.DD.YY
2.7 | Preparation of training material for survey teams (if relevant) | XX | MM.DD.YY | MM.DD.YY
2.8 | Planning of field trip | XX | MM.DD.YY | MM.DD.YY
.
Step 3. Data collection
3.1 | Collect administrative data as defined with stakeholders | XX | MM.DD.YY | MM.DD.YY
3.2 | Conduct training with survey team (if relevant) | XX | MM.DD.YY | MM.DD.YY
3.3 | Field trip as planned | XX | MM.DD.YY | MM.DD.YY
3.4 | Verify quality and consistency of data on a regular basis | XX | MM.DD.YY | MM.DD.YY
3.5 | Obtain and verify final datasets | XX | MM.DD.YY | MM.DD.YY
.
Step 4. Data analysis
4.1 | Clean datasets | XX | MM.DD.YY | MM.DD.YY | [12 empty] | .
4.2 | Refer to 3-D Working Template | XX | MM.DD.YY | MM.DD.YY
4.3 | Refer to the <QS Calculation Sheet for Indicator 1 | XX | MM.DD.YY | MM.DD.YY
4.4 | Refine scoring if needed based on product knowledge | XX | MM.DD.YY | MM.DD.YY
.
Step 5. Formulate recommendations
5.1 | Review gaps identified through analysis and formulate hypothesis | XX | MM.DD.YY | MM.DD.YY
5.2 | Discuss results and hypothesis with stakeholders | XX | MM.DD.YY | MM.DD.YY
5.3 | Formulate recommendations | XX | MM.DD.YY | MM.DD.YY
5.4 | Write final report | XX | MM.DD.YY | MM.DD.YY
5.5
..